## Requirements Traceability Matri
Requirements ID | Requirement | Test Case ID | Test Case Description | Status
701 | Login | 801 | Login - posititive testing | pass
|  | 802 | Login - negative testing | pass
702 | Matrix | 803 | Create a new matrix as manager | issue in code
|  | 804 | Update defects as manager | pass
|  | 805 | Update test cases as manager | issue in code
703 | Navigation | 806 | New links visible as manager | pass
|  | 807 | Back navigation as manager | pass
|  | 808 | All links visible as manager | pass
704 | Test cases | 809 | Add a test case as tester | pass
|  | 810 | Update a test case as tester | pass
|  | 811 | Edit existing test case as tester | issue in code?
|  | 812 | Reset test case as tester | Flaky
705 | Defect | 813 | Assign defect as manager | half-complete code
|  | 814 | Report new defect as manager - positive testing | pass
|  | 815 | Change defect status as tester | mostly complete code
|  | 816 | Steps too short | fail
|  | 817 | Description too short | issue in code
|  | 818 | No date selected | issue in code

## Defects report
Defect ID | Description | Priority | Severity | Test | Status
901 | 812 - Reset test case - "Cannot locate option with value" | Medium | Low | 801 | Pending
902 | 816 - Defects steps too short | Low | Low | 805 | Submitted for Review